## OVERVIEW
MINOR PROJECT MANAGEMENT METHODOLOGY
BACKGROUND
Cloud Counselage delivers many projects for its clients and internally as well. To bring about consistency in the way we deliver our projects, we have developed a project management methodology, which helps our client and our team understand the approach that needs to be taken to deliver these projects. Since these projects vary in duration depending upon its scope, it is practical to take a different approach to deliver projects which are of shorter duration than that taken for the projects of longer duration to bring about efficiencies. In CLoud Counselage, the projects of more than 3 months duration is referred to as major project and that upto 3 months duration is referred as minor project.
OBJECTIVE
The objective of this document is to
PROJECT OVERVIEW
A project is a unique endeavor to produce a set of deliverables within a clearly specified time, cost, and quality constraints. Projects are different from standard business operational activities as they; * Are unique in nature. They do not involve repetitive processes. Every project undertaken is different from the last, whereas the operational activities often involve undertaking repetitive(identical) processes. * Have a defined time scale. Projects have a clearly specified start and end date within which the deliverables must be produced to meet specified customer requirements. * Have an approved budget. Projects are allocated a level of financial expenditure within which the deliverables are produced, to meet a specified customer requirement. * Have limited resources. At the start of a project, an agreed amount of labor, equipment, and materials is allocated to the project. * Involve an element of risk. Projects entail a level of uncertainty and therefore carry business risk. * Achieve beneficial change. The purpose of a project is typically to improve an organization through the implementation of business change.
PROJECT LIFE CYCLE
A project life cycle is the sequence of phases that a project goes through from its initiation to its closure. The number and sequence of the cycle are determined by the management and various other factors like needs of the organization involved in the project, the nature of the project, and its area of application. The phases have a definite start, end, and control point and are constrained by time. The project lifecycle can be defined and modified as per the needs and aspects of the organization. Even though every project has a definite start and end, the objectives, deliverables, and activities vary widely. The life cycle provides the foundation of the actions that have to be performed in the project, irrespective of the specific work involved. The project life cycle generally consists of five phases. They are. PROJECT INITIATION PROJECT PLANNING PROJECT EXECUTION PROJECT CONTROL AND MONITORING PROJECT CLOSURE

## PHASES AND TEMPLATES
PROJECT PHASES AND REQUIRED TEMPLATES
INITIATION PHASE
| REQUIRED TEMPLATE | DESCRIPTION
| PROJECT CHARTER | A project charter formally outlines a project in an organization. It covers the scope of what the project will achieve, as well as the people involved, milestones, budget, and possible risks.
PLANNING PHASE
| REQUIRED TEMPLATE | DESCRIPTION
| PROJECT PLAN | The project plan outlines the course of work for each team member, while keeping the triple constraint of scope, schedule and budget in mind. Project plans describe the processes which will bring the proposal to life.
EXECUTION PHASE
| REQUIRED TEMPLATE | DESCRIPTION
| SRS (DESIGN PHASE) | A software requirements specification (SRS) is a description of a software system to be developed. It lays out functional and non-functional requirements, and may include a set of use cases that describe user interactions that the software must provide.
| DEVELOPMENT LOG (BUILD PHASE) | The development log is used to make a note of all the development changes that are made during the building phase. This log will help you easily handle the different versions of code used for the development.
| TRACEABILITY MATRIX (TEST PHASE) | Traceability Matrix is a really helpful tool to capture the testcase execution progress in one place. It gives management a way to get important Data about Testing.
MONITOR AND CONTROL PHASE
| REQUIRED TEMPLATE | DESCRIPTION
| RAID LOG | A RAID log is a project planning tool for identifying key (R)isks, (A)ssumptions, (I)ssues, and (D)ependencies. At the beginning of the venture, the project team identifies events, activities, and individuals that will or could impact on the successful completion of the project. The RAID log focuses on four key areas: Risks – events that can have an adverse impact if they occur. Assumptions – things you assume are in place which contribute to the success of the project. Issues – current matters that need to be considered and addressed by the group. Dependencies – other projects or triggers that your project depends on, or are a beneficiary of your project outcomes.
CLOSURE PHASE
| REQUIRED TEMPLATE | DESCRIPTION
| LESSONS LEARNED | Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project. They help others learn from the project team’s experience.
SYSTEM GUIDE

## PROJECT CHARTER
PROJECT CHARTER
DOCUMENT VERSION: 1.0
GENERAL PROJECT INFORMATION
PROJECT NAME | Data Science Project
PROJECT SPONSOR | Cloud Counselage Pvt Ltd
PROJECT MANAGER | Jayanth G S
EXPECTED START DATE | 15/06/2020
EXPECTED COMPLETION DATE | 31/07/2020
ESTIMATED COST | None
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE | The main objective of this project is developing accurate and insightful visuallization models. This will help the company to categorize intern's data based on different aspects such as area of interest and learning objectives. Using the dataset provided, a simple model is built to classify the eligibility of intern.
BUSINESS CASE | Internship Program is a noble initiative by Cloud Counselage . Organizations are mainly searching for candidates who are eligible for internship program. Finding candidate who are organization fit is a challenging task. In order to make it easy we have developed a ML model which can predict the best candidates based on the company's parameters efficiently.
GOALS/METRICS | To create an efficient Classifier Model and Visualization Model which will help an organization to classify whether student is eligible or not.
EXPECTED DELIVERABLES | To build an accurate a binary classifier to classify candidate as Eligible/Ineligible along with Data visualization models to build graphs and charts
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE | Machine learning model can be very efficient in automating repetitive elements of the internship/job recruitment process also this can be used for institutional level.
OUTSIDE OF SCOPE | To replace manual CV screening as it is a time-consuming task. So to tackle this issue,more advanced AI-powered CV screening tools can be developed to automatically screen and shortlist new candidates.
PROJECT RESOURCES AND COSTS
PROJECT TEAM | Japesh Gawale
SUPPORT RESOURCES | Working Laptop,Internet,Work Place.
SPECIAL NEEDS | None
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER | Japesh Gawale
KEY STAKEHOLDERS | Jayanth G S, Nirbhey Singh Pahwa
END CUSTOMER | Cloud Counselage
EXPECTED BENEFIT | More successful onboarding rates and increased recruitment of deserving candidates.
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS | Data Quality : This could be an issue when testing of data integration and data cleansing techniques is done on the basis of sample testing, especially when Data is involved. Inadequate Data: The larger the sample size relative to the total population, the greater the confidence in the result, ie, the lower the potential margin of error.
ASSUMPTIONS | Data of candidates provided in the dataset is reliable. Output prediction by model in minimum time.
CONSTRAINTS | Time constraint for project completion.