## Sheet1
PROJECT PLAN FOR EXECUTION PHASE
PROJECT NAME | Data Science Project
PROJECT MANAGER | JAYANTH G S |  | EXECUTION PHASE START DATE: |  | 2020-06-22
PROJECT DELIVERABLE | Clod Counselage Pvt. Ltd. |  | EXECUTION PHASE END DATE: |  | 2020-07-26
PROJECT SCOPE | Select the eligible applicants
PROJECT START DATE | 2020-06-15
PROJECT END DATE | 2020-07-31
OVERALL PROGRESS | Completed
PARENT FEATURE | FEATURES | REQUIRED TIME (IN HRS) | START DATE | END DATE | DURATION IN DAYS | STATUS
1. Initiation | 1.1 Identify Business Probelm | 7 | 2020-06-15 | 2020-06-21 | 7 | COMPLETED
| 1.2 Design model for project | 7 | 2020-06-22 | 2020-06-28 | 7 | COMPLETED
| 1.3 Create a Project charter | 7 | 2020-06-22 | 2020-06-28 | 7 | COMPLETED
| 1.4 Raid log | 7 | 2020-07-06 | 2020-07-12 | 7 | COMPLETED
2. Planning | 2.1 Project Plan | 7 | 2020-05-29 | 2202-07-05 | 7 | COMPLETED
3. Execution | 3.1 Create SRS Document | 7 | 2020-06-22 | 2020-06-28 | 7 | COMPLETED
| 3.2 Development of Project | 7 | 2020-07-06 | 2020-07-12 | 7 | COMPLETED
| 3.3 Update Raid log | 7 | 2020-07-06 | 2020-07-12 | 7 | COMPLETED
| 3.4 Create Development log | 7 | 2020-07-06 | 2020-07-12 | 7 | COMPLETED
| 3.5 Development of Project | 7 | 2020-07-13 | 2020-07-19 | 7 | COMPLETED
| 3.6 Update Raid log | 7 | 2020-07-13 | 2020-07-19 | 7 | COMPLETED
| 3.7 Update Development log | 7 | 2020-07-13 | 2020-07-19 | 7 | COMPLETED
| 3.8 Development of Project | 7 | 2020-07-20 | 2020-07-26 | 7 | COMPLETED
| 3.9 Update Raid log | 7 | 2020-07-20 | 2020-07-26 | 7 | COMPLETED
| 3.10 Update Development log | 7 | 2020-07-20 | 2020-07-26 | 7 | COMPLETED
4. Closure | 4.1 Lessons Learned | 10 | 2020-07-27 | 2020-07-31 | 5 | COMPLETED
| 4.2 Create Detailed Report | 10 | 2020-07-27 | 2020-07-31 | 5 | COMPLETED