## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 4 | 0 | 0 | 0 | 0 | 0
| Project title: | Data Science Project |  | Project Id: |  | Project Manager: | Jayanth G S |  |  | Assumption | 1 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 2 | 0 | 0 | 0 | 0 | 0
|  |  |  | Last Updated date: | 2020-07-30 | Project Team Lead: | Japesh Gawale |  |  | Dependency | 1 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 8 |  |  |  |  | 0
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Improper Analytics | It can lead to false predictions | Analyst should have proper domain knowledge | Japesh Gawale | High |  | Closed | Risk
6 | Risk | Improper data cleaning | Preprocessing will have errors. | Look at the dataset properly and understand it well so that its cleaned properly | Japesh Gawale | Moderate |  | Closed | Open
3 | Assumption | Data is authentic | Work processing would be easier | Check with the source | Cloud Counselage | High |  | Closed | Issue
5 | Risk | Improper model training | Result accuracy will be low | Research well and follow a proper methodology | Japesh Gawale | Critical |  | Closed
6 | Issue | Proper Data Preprocessing | If model contains noise data it can cause problem in evaluation | Proper preprocessing should be done before it is used in model | Japesh Gawale | High |  | Closed | Open
7 | Issue | Choosing the right Algorithm | Use of non-related algorithm will give bad results | We should choose algorithm based on dimensionality, complexity, whether it is classification or rgfression problem | Japesh Gawale | High |  | Closed | Closed
11 | Dependency | Accuracy of model | Wont predict accurate results | Train and tune model properly | Japesh Gawale | High |  | Closed | Moderate
12 | Risk | Issue in IDE | Coding issues | reinstall IDE | Japesh Gawale | Critical |  | Closed | Low
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24